## planning
PLANNING
start date | end date | activity | completion
2026-03-30 | 2026-04-05 | starting the app, learning react | done
2026-04-06 | 2026-04-12 | focus on home page, design changes | done
2026-04-13 | 2026-04-19 | finalize homepage, plan other pages better content wise mostly | done
2026-04-20 | 2026-04-26 | finalize homepage, prototyping, design gallery and fully develop (only frontend) | done
2026-04-27 | 2026-05-03 | prototyping, design profile and helpcenter and fully develop (only frontend), finish gallery | done
2026-05-04 | 2026-05-10 | prototyping, design spotify, tiktok and stepcounter apis (placeholders are okay for now) and fully develop (only frontend), finish gallery, finish itenerary and country pages | in-progress
2026-05-11 | 2026-05-17 | finishing up frontend | to-do
2026-05-18 | 2026-05-24 | start doing backend | to-do
2026-05-25 | 2026-05-31 | backend | to-do
2026-06-01 | 2026-06-07 | backend | to-do
2026-06-08 | 2026-06-14 | backend | to-do
2026-06-15 | 2026-06-21 | backend | to-do
2026-06-22 | 2026-06-28 | connecting backend to frontend | to-do
2026-06-29 | 2026-07-05 | connecting backend to frontend | to-do
2026-07-06 | 2026-07-12 | Finished code | to-do
2026-07-13 | 2026-07-19 | Start marketing | to-do
acceptable delay
1 month

## deadlines
DEADLINES & IMPORTANT DATES
date | activity | completion
2026-05-11 | finished prototype or frontend | in-progress
2026-07-05 | finished plans for marketing | to-be
2026-07-12 | finished code | to-be
2026-07-12 | start marketing/countdown | to-be
2026-07-13 | finished plans for business | to-be

## documents
name | to-do | main deadline | state
MoSCoW? | prepare clear objectives for the project | 2026-04-19 | to-do
prototype | link the prototype in figma that is to be made so that the github repo has a good visualization for interested in the parties | 2026-07-12 | in-progress
README | description of the project, include images, make sure all important stuff are there | 2026-07-12 | in-progress
cookies policies | prepare legal documents for cookies | before release | in-progress
licences | ensure all images, apis, and other licenses are named in a appropriate manner | before release | to-do
resources | ensure all images, apis, and other licenses are on the website shown and available to see for all in a appropriate manner | before release | to-do
marketing proposal | make a marketing proposal for the companies you would like to sponsor you | 3-6 months in | to-do

## marketing ideas
name | to-do | main deadline | state | tools
mascot | create a persona that will promote the brand and also be in-app as a helper | before finishing code | to-do | ai
choose the medium | research instagram, twitter and tiktok to decide what is better to promote the project | before release | to-do | research
plan strategy | one colored content, the visual stuff | before planning posts | to-do | canva, pinterest
plan posts | plan at least 10 posts before releasing so that you can be prepared | before release | to-do | canva
organize logo creation | contact nina, kinga or use ai | before finishing code | to-do | ai, people
releasing a beta version | first release being a beta version for a limited number of users, the ones who sign up to it (first 50 users) get free premium for life | after finishing code | to-do
getting users | first 100 users of the app get free premium for life | after finishing code | to-do
linkedin | post on linked in. decide if finished, accomplished product or only when finished | to-be decided | to-do | linkedin
influencers | consider contacting travel influencers to promote the app, focus on small ones so that they wont need money | 3 months app runing | to-do | medium
choose target audience | choose and document the target audience you want to reach. Make it clear and simple but also specific | 2026-04-19 | to-do | canva
plan user costs | see how much you spend from the app, how much you want to earn, how many users you expect, how much other apps like that cost | before release | to-do
plan promotions | decide which promotions/special offers make sense for this project, how much of a discount, when, when someone is close but goes back more discount, newsletter discount | before release | to-do
decide on cost of premium | decide how much should the user spend on premium and how should that change, also monitor the site and adjust accordingly | before release | to-do
decide when to start marketing | either start marketing before the official release (decide how early), or to start when its already out (harder but maybe makes more sense) | before finishing code | in-progress
contact sponsors/ads | consider google ads, travelling companies etc, decided based on income sheet/costs, filter through so no weird shit, aim for travelling and hotel companies | 3-6 months app running | to-do | google ads
premium features trial | the user has an option to try the premium for f.ex a month, decide how long, monitor how many decide to stay with premium after the trial | before release | to-do
plan campaigns | for easter/christmas or more for specific countries add some features like stickers (look at canva) both to code and marketing medium | before finishing code | to-do | code, medium
friend recommendations | after you recommend the app to the friend you get a free premium for a month or so | before finishing code | to-do
consider contacting erasmus | consider connecting about sponsorship/ads, make a proposal, make sure its legally good | 1-2 months app running | to-do | word
communication with customers | ensure customer engagement, decide how, maybe premium users have more options | before release | to-do

## features ideas
name | to-do | deadline | state
want to visit countries/cities | planning the trips, make a skeleton for full itenerary, automated process but one that allows a lot of customization, look at your itenerary Notion pages | 2026-04-19 | in-progress
gallery | view all photos from trips, make a randomizer, quizz where the picture was from, upload but also automatical access to the gallery so it can be saved in app if possible | 2026-04-26 | in-progress
profile | basic info, settings | 2026-05-03 | in-progress
helpcenter | faq from document, contact support, chatbot? | 2026-05-03 | in-progress
tiktok api | tikto videos matching to selected locations | 2026-05-10 | to-do
spotify api | playlist for each location/city, either already made playlists or make spotify do them, make 2 playlists: for the trip and after, the one after is the songs you listened to during the trip ordered by how many times you listened to them | 2026-05-10 | to-do
stepcounter api | for each trip and each day of it have a stepcounter, sth like strava | 2026-05-10 | to-do
llm chat bots? | support bots, idk if its worth doing, consider usefulness, pricing, and product image | 2026-07-05 | to-do
friend recommendations | after you recommend the app to the friend you get a free premium for a month or so | before finishing code | to-do
design 2 versions | make a modern (grey) and og (brown) design, test both versions, see which does better | before finishing code | in-progress
more animations | animate the content to be more cute and fun, look at stanleys site | before finishing code | in-progress
prototype | prototype all the pages then add updates to specific pages | update till the end | in-progress
notes/diary from trips | allow a little diary for each trip, save date text, have recaps like on snap, allow some stickers that match the place, add printability | after finished coding | in-progress
hotel booking | if and when profitable talk to booking com or sth | after getting sponsors | to-do
homepage | search countries, globe, select country status, status overview | 2026-04-26 | in-progress

## pages-frontend
helpcenter | welcome | home | gallery
add searchbar for faq | remove circle | change open button to sth else | load time
show all categories (more like studytracker) | functionality | unify status colors throughout page and website | heic files
arrow to scroll to top |  | make height of right div (next to map) smaller to fit contents + padding | upload photos button
contact support container layout |  | fix globe transparency (right now the globe view is slightly transparent. I want 100 opacity | remove bottom/horizontal scroll
contact support functionality |  | make flat map view min zoom fit all countries on the map | remove the reload of the pictures (load once)
more questions |  | revert the map to the previous version | use ai or other api to add automatical captions/alt text to photos and add location tags to all
when using nav bar from gallery its slow or not working unless manual reload, which needs to be fixed
country | itenerary | profile | settings
make the nav bar heading scroll to the list on homepage or some other better view of all the countries that needs to be created | change style completely | change settings and help center buttons to be icons instead of text and style them appropriately | account change password
add notes section that has notes from itenerary | make the checklist customizable, as well as basically any other list | avatar change to be saved in backend (later) | delete account
make the globe smaller | add bookings functionality (either separate page or sth in page) | logout button functionality (for now go to welcome page and log out) | remove last locally saved at
plan itenerary button should scroll to the section with iteneraries | add day plan functionality as in notion | delete profile option (navigate to settings account options) | add a settings icon in footer nect to helpcenter one
the status tag should be styled differently | add a packing list with pre-made categories turn on/off option | add subscription status | notifications email and push selection
api integrations functionality and if free plan blurred and not available (add link to settings to change your plan), but for premium not | add import from another trip option for all things | style status tiles better (visited etc) | notifications functionality
iteneraries section views | add full CRUD | edit profile navigate to settings to account options | premium changes alert messages
gallery remove text and number on photos. Add date added instead | add new itenerary shouldn’t be in here, it should be in the country |  | plans details information (free includes this, premium includes that) plans: free, monthly, yearly, free trials (custom, for now 1 week or 1 month), lifetime. Users cannot change their plans through select dropdown
show first 15 photos in gallery after that add a long button (simmilar to search bar but using brown color) that says long more | make it look like the notion page (uploaded pdf) |  | plans details styling simmilar to chatgpt one
the current load button (tile-sized) should be and upload photo(s) button | ensure photos (gallery) load the same way as in Gallery |  | payment implementations: paypal, apple pay, google pay, credit card, ideal
style the itenerary section like the bottom one then remove the bottom one |  |  | invoice management
gallery highlight should have no buttons, just automatic scroll and on click it should go to gallery to that specifix picture and open modal from there |  |  | about & policies change to about and there add a link to policies and other informations about app (simmilar to readme)
change heading
add a notes in itenerary to inlude any written text (also add ai scanning of actual notes) with appropriate handwriting but including different languages fonts that users can scan and ai can process and upload as text. Add functionality as well
style better for no data (like no photos, no iteneraries etc.)
policies
update styling
update policies text before finishing the full app

## backend
programming language | vercel | spotify api | stepcounter api | tiktok videos
db management | superbase | create or take created playlists for each country/city |  | look for videos on tiktok with #CountryName or #CityName for each city/country and put them to see
erd | in readme resources
user monitoring | posthog
user management | payment management | general to-do
login through google | security and encryption must be ensured | crud updated to db
login through facebook | functionality | gallery to db to specific user
login with email + password | different plans == different prices | login through google
security and encryption must be ensured |  | login through facebook
email, password, pfp, plan, visited countries + other statuses, gallery |  | publishing the app
use as guest |  | app logo
posthog
ask users loging in with email for name
settings edit db update
stripe functionality
globe fuckery

## business side
name | to-do | main deadline | state
documentation | all needed docummentation is available, proper, github repo, README but also release shit | before release | to-do
cookies | cookie policies are formatted correctly and legally okay | before release | to-do
licences | all images, apis need to have an open license for commercial use, if needed to pay switch the resource if possible | before release | to-do
policies | all policies of use in app need to be done correctly | before release | to-do
premium costs | use stipe, calculate costs, how many users you want, how does the market look like to make the app profitable but also attractive, focus on sales not profit | before release | to-do
taxes | read up on how to deal with taxes in case you have income, then follow up and do them | before release | to-do
api pricings | if api is free to use make sure its also for commercial use, if not consider if its worth it | before finished coding | to-do
backend costs? | if backend making costs idk do sth | before starting backend | to-do
<a href="https://www.maptiler.com/copyright/" target="_blank">&copy; MapTiler</a> <a href="https://www.openstreetmap.org/copyright" target="_blank">&copy; OpenStreetMap contributors</a>